## Cover Page
IoT Course
Capstone Project
Work Breakdown Structure
For students
ⓒ2023 SAMSUNG. All rights reserved.
Samsung Electronics Corporate Citizenship Office holds the copyright of this document.
This document is a literary property protected by copyright law so reprint and reproduction without permission are prohibited.
To use this document other than the curriculum of Samsung Innovation Campus, you must receive written consent from copyright holder.
Samsung Innovation Campus

## WBS
Capstone Project Work Breakdown Structure (WBS)
Done
In-progress
Delayed
Today | 2024-07-28
Project Team Name | IOT1 ICTU
Project Topic | Smart Home Automatic Control of Fan and LED Lights
Task |  | Start date | End date | Responsibility | Deliverable | Task Status | W1 |  |  |  |  | W2 |  |  |  |  | W3 |  |  |  |  | W4
[7 empty] | D1 | D2 | D3 | D4 | D5 | D6 | D7 | D8 | D9 | D10 | D11 | D12 | D13 | D14 | D15 | D16 | D17 | D18 | D19 | D20
[7 empty] | 2021-11-01 | 2021-11-02 | 2021-11-03 | 2021-11-04 | 2021-11-05 | 2021-11-06 | 2021-11-07 | 2021-11-08 | 2021-11-09 | 2021-11-10 | 2021-11-11 | 2021-11-12 | 2021-11-13 | 2021-11-14 | 2021-11-15 | 2021-11-16 | 2021-11-17 | 2021-11-18 | 2021-11-19 | 2021-11-20
1.1.Used GitHub |  | 2024-07-15 |  |  |  | Done | bar: 2021-11-01 to 2021-11-13
1.2. Explored GPIO pins and datasheet of Raspberry Pi | [5 empty] | Done | bar: 2021-11-01 to 2021-11-12
1.3. Learned Python language | [5 empty] | Done | bar: 2021-11-01 to 2021-11-08
1.4. Studied VSCode programming environment | [5 empty] | Done | bar: 2021-11-01 to 2021-11-06
1.5. Implemented a button to control 3 LEDs and the HC05 sensor module |  |  | 2024-07-28 |  |  | Done
2.1. Prepared necessary components |  | 2024-07-29 |  |  |  | In-progress
2.2. Developed algorithm flowchart and block diagram | [5 empty] | In-progress
2.3. Researched connection methods |  |  | 2024-08-04 |  |  | In-progress
In-progress
In-progress
In-progress
In-progress
In-progress
In-progress
In-progress
In-progress